## Matrix
RAM Matrix
JC Consulting Client
Roles and Responsibilities
|  | ROLES | Renata | Abdalaham | Anuska
| Deliverable or Task | Status
Admin Pages
| Home Page | Completed | R | A
| Insert New User | On going | R | A
| User List | On going | R | A
| User Details | On going | R | A
| Company List | On going | R | A
| Company Details | On going | R | A
| Job List |  | A | A | R
| Job Details |  | A | A | R
Client Pages
| Home Page | On going | A | R
| Register | On going | A | R
| Add | On going | A | R
| Add New Job | On going | A | R
| Job Details | On going | A | R
| Edit Jobs | On going | A | R
Sprint 8
| Minutes of Meeting | Completed | R | A
| Status Report | Completed | R | A
Testing and Debugging
| Test | On going | R | R | R
Backed
| Admin | On going | A | R
| Client | On going | A | R
Percentage Assigned
|  |  | 50% | 45%
Insert new rows above this one
R | Responsible
A | Assist
C | Consulted